## 00 Index
Change Control Toolkit
Change Control ¦ DeliverIQ Open PM Toolkit - Area Workbook
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Sheet | Template | Purpose
01 Simple Change Request | Starter | Single-form request for a scope, schedule or cost change.
02 Full Change Impact Assessmen | Professional / AI-ready | Multi-dimension impact scoring before a change is approved.
03 Change Control Board Pack | Executive | Options analysis and recommendation for the CCB to decide.
04 Agile Scope Change Log | Agile | Backlog-level scope changes and Product Owner decisions.
05 Change Log (Master Index) | Reference | Single running index of every CR raised, for traceability.
06 CCB Meeting Minutes Template | Operational | Structured record of each Change Control Board meeting.
07 Change Impact Scoring Guide | Reference | Thresholds that decide which approval route a change takes.

## 01 Simple Change Request
Simple Change Request
Change Control ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Change ID | Change | Reason | Requested By | Owner | Status | Decision
CR-001 | Example scope change | Regulatory update requires new field | Business Analyst | Project Manager | Proposed | -
CR-002 | Extend UAT window by 3 days | Additional defect fix cycle needed | QA Lead | Delivery Lead | Approved | Approved 2026-09-10

## 02 Full Change Impact Assessmen
Full Change Impact Assessment
Change Control ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Change ID | Scope Impact | Schedule Impact (Days) | Cost Impact | Capacity Impact | Risk Impact | Benefit Impact | Recommendation | Decision
CR-001 | Adds one new data field to migration mapping | 2 | 5000 | 0.2 FTE for 1 week | Low - well understood change | Neutral | Assess | -
CR-002 | No scope change - testing window only | 3 | 0 | None | Reduces UAT risk | Positive - fewer post go-live defects | Approve | Approved

## 03 Change Control Board Pack
Change Control Board Pack
Change Control ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Change | Business Need | Option A | Option B | Impact Summary | Recommendation | Decision
Example change | Regulatory field required for go-live | Add field now (2-day slip) | Add field post go-live (compliance risk) | Option A protects compliance at minor schedule cost | Option A | -

## 04 Agile Scope Change Log
Agile Scope Change Log
Change Control ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Change | Epic / Feature | Reason | Priority Shift | Sprint Impact | Product Owner Decision | Status
Example feature change | Reporting Layer | User feedback from beta | Raised to P1 | Adds to Sprint 5 | Accepted | Proposed

## 05 Change Log (Master Index)
Change Log (Master Index)
Change Control ¦ Running index of every CR raised, pulled together for traceability
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Change ID | Title | Type | Date Raised | Current Status | Final Decision
CR-001 | Example scope change | Simple CR | 2026-09-05 | Proposed | -
CR-002 | Extend UAT window by 3 days | Simple CR | 2026-09-08 | Approved | Approved 2026-09-10

## 06 CCB Meeting Minutes Template
CCB Meeting Minutes Template
Change Control ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Field | Detail
Meeting Date | 2026-09-12
Attendees | Sponsor; PM; Delivery Lead; Tech Lead; QA Lead
Changes Reviewed | CR-001, CR-002
CR-001 Outcome | Deferred - request further cost detail before next CCB
CR-002 Outcome | Approved - implement immediately
Actions Arising | PM to return with refined cost estimate for CR-001 by 2026-09-19
Next CCB Date | 2026-09-19

## 07 Change Impact Scoring Guide
Change Impact Scoring Guide
Change Control ¦ Reference - what approval route a change should take
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Impact Level | Typical Threshold | Approval Route
Minor | No schedule/cost impact, no scope change | Project Manager can approve directly
Moderate | Up to 5 days schedule slip or up to 5% budget | Delivery Lead approval, logged in Change Log
Major | More than 5 days slip, more than 5% budget, or scope change | Full impact assessment + Change Control Board decision
Critical | Threatens go-live date, regulatory commitment, or budget approval limit | Sponsor / Programme Board decision required