## 00 Index
Cutover & Release Toolkit
Cutover & Release ¦ DeliverIQ Open PM Toolkit - Area Workbook
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Sheet | Template | Purpose
01 Cutover Checklist | Starter | Sequenced high-level cutover task list.
02 Detailed Cutover Runbook | Professional / AI-ready | Minute-by-minute execution runbook with rollback per step.
03 GoNoGo Readiness | Executive | Go/No-Go criteria and sign-off for the cutover decision.
04 Hypercare Tracker | Professional / AI-ready | Post-go-live issue tracking during the hypercare window.
05 Rollback Decision Guide | Reference | Trigger criteria and roles for invoking rollback.
06 Cutover Communication Plan | Deep-dive | Who is told what, at which point in the cutover, via which channel.
07 Environment Readiness | Deep-dive | Pre-cutover technical readiness sign-off by environment.

## 01 Cutover Checklist
Cutover Checklist
Cutover & Release ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Seq | Task | Owner | Planned Start | Planned End | Validation | Status
1 | Confirm backup | Infra Lead | 2026-10-01 20:00 | 2026-10-01 20:30 | Backup verified | Planned
2 | Freeze source systems | Release Lead | 2026-10-01 20:30 | 2026-10-01 20:45 | Freeze confirmed by all teams | Planned
3 | Run migration scripts | Data Lead | 2026-10-01 20:45 | 2026-10-01 22:00 | Row counts match source | Planned
4 | Smoke test | QA Lead | 2026-10-01 22:00 | 2026-10-01 22:30 | Critical paths pass | Planned
5 | Go-live announcement | Release Lead | 2026-10-01 23:00 | 2026-10-01 23:15 | Comms sent | Planned

## 02 Detailed Cutover Runbook
Detailed Cutover Runbook
Cutover & Release ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Step | Activity | Start | Duration (min) | Owner | Dependency | Validation | Rollback | Status
1 | Freeze source | 20:30 | 15 | Release Lead | - | Freeze confirmed | Unfreeze | Planned
2 | Take final backup | 20:45 | 20 | Infra Lead | Freeze source | Backup checksum matches | Restore from prior backup | Planned
3 | Run migration batch 1 | 21:05 | 45 | Data Lead | Backup complete | Row count reconciliation | Restore backup; retry batch | Planned
4 | Run migration batch 2 | 21:50 | 45 | Data Lead | Batch 1 validated | Row count reconciliation | Restore backup; retry batch | Planned
5 | Smoke test critical paths | 22:35 | 30 | QA Lead | Migration complete | Test pack pass rate 100% | Trigger Go/No-Go rollback call | Planned

## 03 GoNoGo Readiness
Go-No-Go Readiness
Cutover & Release ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Criterion | Evidence | Owner | Status | Exception | Decision
UAT exit approved | UAT sign-off document | Business Lead | Amber | 2 low-severity defects deferred | Pending
Backup & rollback tested | Rollback rehearsal log | Infra Lead | Green | - | Go
Comms plan ready | Communication Plan tab | Release Lead | Green | - | Go
Support rota staffed | Hypercare roster | Support Lead | Green | - | Go

## 04 Hypercare Tracker
Hypercare Tracker
Cutover & Release ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Issue | Severity | Owner | Opened | Workaround | Resolution | Status
Example production issue | Medium | Support Lead | 2026-10-02 | Manual reprocessing | Fix scheduled next release | Open
Slow report load on go-live day | Low | Support Lead | 2026-10-02 | Off-peak refresh | Index optimisation applied | Closed

## 05 Rollback Decision Guide
Rollback Decision Guide
Cutover & Release ¦ Reference - when and how to invoke rollback
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Trigger | Action
Data reconciliation variance exceeds agreed tolerance | Halt cutover; Release Lead convenes Go/No-Go call within 15 minutes.
Critical smoke test fails | Do not proceed to announcement; invoke rollback for the affected component.
Rollback window at risk of closing | Escalate to Sponsor immediately - decision cannot wait for next checkpoint.
Role | Rollback Authority
Release Lead | Can pause cutover and initiate technical rollback.
Sponsor | Sole authority to accept residual risk and proceed despite an Amber/Red criterion.
Business Lead | Confirms business impact of rollback vs proceeding.

## 06 Cutover Communication Plan
Cutover Communication Plan
Cutover & Release ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Trigger Point | Audience | Message | Channel | Owner | Timing
Cutover start | All stakeholders | Cutover has begun; system read-only | Email + Status page | Release Lead | T-0
Go decision confirmed | SteerCo | Go/No-Go decision and rationale | SteerCo call | Sponsor | T+2h
Go-live complete | All users | System live; support contact details | Email + Intranet banner | Release Lead | T+3h
Rollback invoked (if needed) | All stakeholders | Rollback in progress; next update time | Email + Status page | Release Lead | Immediate

## 07 Environment Readiness
Environment Readiness Checklist
Cutover & Release ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Environment | Readiness Item | Owner | Status | Evidence
Production | Capacity headroom confirmed | Infra Lead | Complete | Capacity report
Production | Monitoring & alerting live | Infra Lead | Complete | Dashboard link
DR / Failover | Failover tested within 90 days | Infra Lead | In Progress | Failover test log
Support Tooling | Ticketing queue configured for hypercare | Support Lead | Complete | Queue screenshot