## 00 Index
Dependencies Toolkit
Dependencies ¦ DeliverIQ Open PM Toolkit - Area Workbook
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Sheet | Template | Purpose
01 Basic Dependency Register | Starter | Single-project log of what you are waiting on from others.
02 CrossTeam Dependency Register | Professional / AI-ready | Multi-attribute register for tracking dependencies between teams.
03 Programme Dependency Heatmap | Executive | Roll-up view of the riskiest cross-project dependencies for leadership.
04 Dependency Impact Assessment | Professional / AI-ready | Models the knock-on effect if a specific dependency slips.
05 Dependency Scoring Guide | Reference | How to score criticality, set RAG thresholds, and read the heatmap.
06 Escalation & SLA Tracker | Operational | Tracks who a dependency was escalated to, when, and against what SLA.
07 Dependency Health Dashboard | Analysis | Live counts and RAG split calculated from the registers, by formula.

## 01 Basic Dependency Register
Basic Dependency Register
Dependencies ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Dependency | Provider | Consumer | Owner | Due Date | Status
API certification | Platform Team | Migration Team | Delivery Lead | 2026-10-01 | Open
Test environment refresh | Infrastructure | QA Team | QA Lead | 2026-09-20 | In Progress
Legal sign-off on data use | Legal | Data Team | Project Manager | 2026-09-25 | Open
Vendor licence renewal | Procurement | Delivery Team | Delivery Lead | 2026-10-10 | At Risk
Content migration script | Engineering | Content Team | Tech Lead | 2026-09-18 | Closed

## 02 CrossTeam Dependency Registe
Cross-Team Dependency Register
Dependencies ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Dependency | Provider Team | Consumer Team | Dependency Type | Owner | Due Date | Criticality | Impact | Escalation | Status
Data feed certification | Platform | Migration | Technical | Delivery Lead | 2026-09-30 | High | May delay UAT exit | Programme | Open
Shared identity service | Platform | Migration | Technical | Tech Lead | 2026-10-05 | High | Blocks login testing | Programme | In Progress
Finance reconciliation rules | Finance | Data | Process | Data Lead | 2026-09-22 | Medium | Delays sign-off | Project | Open
Third-party API rate limits | Vendor | Engineering | External / Vendor | Tech Lead | 2026-10-12 | Critical | Blocks go-live load test | Programme | At Risk

## 03 Programme Dependency Heatmap
Programme Dependency Heatmap
Dependencies ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Project | Dependency | Upstream | Downstream | Criticality | Due Date | Days at Risk | Executive Action
Migration | Identity API | Platform | Migration | High | 2026-09-30 | 0 | Confirm recovery plan
Migration | Finance feed | Finance | Data | Critical | 2026-09-22 | 3 | Escalate to Finance SteerCo
Platform Uplift | Network cutover window | Infrastructure | Platform | Medium | 2026-10-15 | 0 | Monitor

## 04 Dependency Impact Assessment
Dependency Impact Assessment
Dependencies ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Dependency | Slip Scenario (Days) | Milestones Affected | Projects Affected | Risk Exposure | Mitigation | Decision Required
Identity API | 14 | UAT Exit; Cutover Rehearsal | Migration | High | Parallel validation path | Approve contingency
Finance feed | 7 | Reconciliation Sign-off | Data; Finance | High | Manual reconciliation fallback | Approve manual process
Vendor licence renewal | 5 | Go-live Readiness Review | Delivery | Medium | Extend interim licence | None - in progress

## 05 Dependency Scoring Guide
Dependency Scoring & RAG Guide
Dependencies ¦ Reference Guide - how to score and colour-code dependencies
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Criticality | Definition | RAG Guidance
Low | Delay would not affect any committed milestone; workaround is trivial. | Green - track at team level only.
Medium | Delay of 1-5 days is absorbable inside existing schedule float. | Green/Amber - review weekly.
High | Delay directly threatens a committed milestone or go-live date. | Amber - report weekly to programme; assign named owner and mitigation.
Critical | Delay stops a workstream entirely or breaches a contractual/regulatory date. | Red - escalate immediately; requires executive decision within 48 hours.
Days at Risk | Meaning
0 | On track against the due date recorded in the register.
1-3 | Minor slippage - monitor, no escalation required yet.
4-7 | Material slippage - notify dependency owner and consumer team lead.
8+ | Severe slippage - escalate to the Programme/SteerCo level and log a Decision Required.

## 06 Escalation & SLA Tracker
Escalation & SLA Tracker
Dependencies ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Dependency | Escalated By | Escalated To | Escalation Date | SLA to Respond (Days) | Response Due | Response Received | Outcome | Status
Finance feed | Data Lead | Finance Director | 2026-09-14 | 2 | 2026-09-16 |  |  | Open
Identity API | Tech Lead | Platform Head | 2026-09-10 | 3 | 2026-09-13 | 2026-09-13 | Recovery plan agreed | Closed

## 07 Dependency Health Dashboard
Dependency Health Dashboard
Dependencies ¦ Live counts calculated from the Cross-Team Register
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Metric | Value
Total dependencies logged | 4
Open | 2
In Progress | 1
At Risk | 1
Blocked | 0
Critical criticality open items | 1