## 00 Index
Planning Toolkit
Planning ¦ DeliverIQ Open PM Toolkit - Area Workbook
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Sheet | Template | Purpose
01 Project Charter | Starter | Foundational one-page mandate: purpose, scope, governance.
02 Delivery Plan | Professional / AI-ready | Workstream-level milestones, owners and dates.
03 90Day Mobilisation Plan | Leadership | First-90-days plan for standing up a new project or team.
04 Hybrid Project Plan | Hybrid | Blends waterfall phases with agile epics/sprints.
05 Milestone Schedule (Gantt-style) | Deep-dive | Sequenced milestones with dependencies and duration.
06 Resource Plan | Deep-dive | Role-level allocation, FTE %, and start/end dates.
07 Assumptions & Constraints | Reference | Dedicated, fuller version of the Charter's assumptions section.

## 01 Project Charter
Project Charter
Planning ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Section | Detail
Purpose | Migrate core platform to reduce operating cost and improve reliability.
Business Outcome | 20% reduction in incident volume; 15-minute faster reporting cycle.
Objectives | 1) Migrate data with zero critical defects. 2) Decommission legacy platform by Q1.
In Scope | Core data migration, user access, reporting layer.
Out of Scope | New feature development; third-party integrations beyond current state.
Success Measures | Zero P1 defects at go-live; reconciliation variance < 0.1%.
Key Milestones | Design freeze - UAT entry - Go-live - Hypercare exit.
Governance | Weekly working group; fortnightly SteerCo; monthly Programme Board.
Assumptions | Test environments available from Sprint 3; vendor SLA holds.
Constraints | Fixed regulatory go-live date; capped migration budget.

## 02 Delivery Plan
Delivery Plan
Planning ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Workstream | Milestone / Deliverable | Owner | Start Date | Finish Date | Dependency | Status | RAG
Data | UAT Exit | Data Lead | 2026-09-01 | 2026-09-22 | Finance feed certification | Not Started | Amber
Platform | Environment Build | Infra Lead | 2026-08-15 | 2026-09-05 | - | Complete | Green
Testing | UAT Cycle 1 | QA Lead | 2026-09-08 | 2026-09-19 | Environment Build | In Progress | Amber
Cutover | Go-Live | Release Lead | 2026-10-01 | 2026-10-02 | UAT Exit; Go/No-Go approval | Not Started | Green

## 03 90Day Mobilisation Plan
90-Day Mobilisation Plan
Planning ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Period | Objective | Deliverables | Stakeholders | Risks | Measures
Days 1-30 | Mobilise | Team onboarded; charter approved; governance cadence live | Sponsor; PMO | Resourcing delay | 100% roles filled
Days 31-60 | Plan & Design | Delivery plan baselined; architecture approved | Architecture; Business | Scope creep | Plan sign-off achieved
Days 61-90 | Build & Validate | Environment ready; first UAT cycle complete | QA; Vendor | Environment slippage | UAT entry criteria met

## 04 Hybrid Project Plan
Hybrid Project Plan
Planning ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Phase | Epic / Work Package | Milestone | Sprint / Date | Owner | Acceptance Criteria | Status
Discovery | Requirements | Scope baseline | Sprint 0 | PM | Sponsor approval | Not Started
Build | Core Migration Engine | Feature complete | Sprint 1-4 | Tech Lead | All unit tests pass | In Progress
Stabilise | UAT & Defect Fix | UAT exit | Sprint 5-6 | QA Lead | Zero P1/P2 defects open | Not Started

## 05 Milestone Schedule (Gantt)
Milestone Schedule (Gantt-style)
Planning ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Milestone | Predecessor | Planned Start | Planned End | Duration (Days) | Owner | Status
Design Freeze | - | 2026-08-25 | 2026-08-29 | 4 | Architect | Complete
Environment Ready | Design Freeze | 2026-09-01 | 2026-09-05 | 4 | Infra Lead | Complete
UAT Entry | Environment Ready | 2026-09-08 | 2026-09-08 | 0 | QA Lead | In Progress
UAT Exit | UAT Entry | 2026-09-08 | 2026-09-22 | 14 | QA Lead | Not Started
Go-Live | UAT Exit; Go/No-Go | 2026-10-01 | 2026-10-02 | 1 | Release Lead | Not Started

## 06 Resource Plan
Resource Plan
Planning ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Role | Named Resource | Workstream | Allocation % | Start Date | End Date | Notes
Project Manager | TBC | All | 100% | 2026-08-01 | 2026-10-31 | Full-time for duration
Data Lead | TBC | Data | 100% | 2026-08-01 | 2026-10-15 | Ramps down post-hypercare
QA Lead | TBC | Testing | 80% | 2026-08-15 | 2026-10-15 | 80% - shared with BAU

## 07 Assumptions & Constraints
Assumptions & Constraints Log
Planning ¦ Reference - fuller version of the Charter's assumptions section
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Type | Statement | Owner | Confidence | Validation Plan | Impact if Wrong
Assumption | Test environments available from Sprint 3 | Infra Lead | Medium | Confirm environment booking by Sprint 1 | UAT delayed by 1-2 sprints
Constraint | Fixed regulatory go-live date | Sponsor | High | N/A - external mandate | Non-negotiable; drives all sequencing
Assumption | Vendor SLA holds through migration window | Delivery Lead | Medium | Reconfirm SLA in vendor check-in | Cutover window at risk