## 00 Index
RACI Toolkit
RACI ¦ DeliverIQ Open PM Toolkit - Area Workbook
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Sheet | Template | Purpose
01 Basic RACI Matrix | Starter | Simple activity-by-role responsibility matrix.
02 Project Governance RACI | Professional / AI-ready | Deliverable-level RACI across the full governance structure.
03 Programme RACI | Executive | Decision rights across programme-level roles and SteerCo.
04 Agile Team RACI | Agile | Scrum-team responsibility split for common agile ceremonies/artefacts.
05 RACI Facilitation Guide | Reference | Rules for building a valid RACI and running the workshop.
06 RACI Validation Checklist | Reference | Automated-style checks to catch the most common RACI mistakes.
07 Decision Rights Matrix | Deep-dive | Extends RACI with Recommend/Decide/Perform for high-stakes calls (RAPID-style).

## 01 Basic RACI Matrix
Basic RACI Matrix
RACI ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Activity | Responsible | Accountable | Consulted | Informed
Project Charter | Project Manager | Sponsor | Delivery Lead | Stakeholders
Risk Register Maintenance | Project Manager | Delivery Lead | Risk Owners | SteerCo
Status Report | Project Manager | Delivery Lead | Workstream Leads | Stakeholders

## 02 Project Governance RACI
Project Governance RACI
RACI ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Deliverable | Sponsor | Project Manager | Delivery Lead | Business | Technology | Vendor | PMO
Project Charter | A | R | C | C | I | I | C
Business Case | A | C | I | R | I | I | C
Delivery Plan | I | A | R | C | C | C | I
Go-Live Decision | A | R | C | C | C | I | I

## 03 Programme RACI
Programme RACI
RACI ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Decision / Outcome | Programme Director | Project Leads | Architecture | Finance | Risk | SteerCo
Programme funding change | R | C | C | C | C | A
Cross-project re-sequencing | A | R | C | I | C | I
Go/No-Go for release | R | C | C | I | C | A

## 04 Agile Team RACI
Agile Team RACI
RACI ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Activity | Product Owner | Scrum Master | Developers | Architect | Business
Sprint Goal | A | C | R | C | C
Backlog Refinement | A | C | R | C | I
Sprint Retrospective | I | A | R | C | I
Release Decision | A | C | C | R | C

## 05 RACI Facilitation Guide
RACI Facilitation Guide
RACI ¦ Reference Guide - roles and workshop steps
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Letter | Meaning
R | Responsible - does the work to complete the activity. Can be shared, but ownership of the outcome sits with A.
A | Accountable - owns the outcome and sign-off. Exactly one A per row, always.
C | Consulted - two-way input before the decision or deliverable is finalised.
I | Informed - kept up to date after the decision, one-way communication.
Workshop Step | What Happens
1. List activities | Capture every deliverable or decision that needs an owner - not tasks.
2. List roles | Use role titles, not named individuals, so the matrix survives staff changes.
3. Assign A first | Agree who is accountable for each row before assigning R, C, I.
4. Sanity-check | Run the validation checklist (tab 06) before circulating for sign-off.
5. Socialise & baseline | Share with all named roles, capture sign-off, and version the matrix.

## 06 RACI Validation Checklist
RACI Validation Checklist
RACI ¦ Common mistakes to check for before sign-off
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Check | Why It Matters
Exactly one A per row | Two or more A's means no one is truly accountable when it counts.
Every row has at least one R | A deliverable with no Responsible party will not get done.
No role is R or A on everything | Signals an over-centralised structure and a single point of failure.
C is used sparingly | Too many C's slows decisions down; only consult where input changes the outcome.
I list is reviewed, not assumed | Being 'informed' on everything creates noise and email fatigue.
Matrix is dated and versioned | RACI drifts as teams change; review at each phase gate.

## 07 Decision Rights Matrix
Decision Rights Matrix (RAPID-style)
RACI ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Decision | Recommend | Agree | Perform | Input | Decide | Notes
Vendor selection | Procurement Lead | Legal | Delivery Team | Finance | Sponsor | Used for high-value or irreversible calls
Architecture standard | Chief Architect | Security | Engineering | Delivery Leads | CTO