## 00 Index
RAID Toolkit
RAID ¦ DeliverIQ Open PM Toolkit - Area Workbook
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Sheet | Template | Purpose
01 Simple RAID Log | Starter | Single flat list of Risks, Assumptions, Issues and Dependencies.
02 Scored RAID Register | Professional / AI-ready | Adds probability x impact scoring and RAG to prioritise items.
03 Executive RAID Summary | Executive | Top items only, framed as business impact for leadership.
04 Technical Migration RAID | Specialist | Domain-specific RAID for technical / data migration risk.
05 RAID Scoring Guide | Reference | Probability/impact scale, scoring matrix, and RAID definitions.
06 Assumptions Log | Deep-dive | Dedicated tracker for assumptions - the most-neglected RAID category.
07 RAID Trend Tracker | Analysis | Week-over-week counts by type and RAG, calculated by formula.

## 01 Simple RAID Log
Simple RAID Log
RAID ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Type | Title | Owner | Status | Due Date
Risk | Example delivery risk | Project Manager | Open | 2026-10-01
Assumption | Test data will mirror production volumes | QA Lead | Open
Issue | UAT environment unavailable for two days | Infra Lead | In Progress | 2026-09-18
Dependency | Vendor sign-off on integration spec | Delivery Lead | Open | 2026-09-25

## 02 Scored RAID Register
Scored RAID Register
RAID ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Type | Title | Probability (1-5) | Impact (1-5) | Score | RAG | Owner | Mitigation | Target Date | Escalation
Risk | Source extract delay | 3 | 4 | 12 | Amber | Data Lead | Run extract rehearsal | 2026-09-20 | Programme
Risk | Key resource attrition | 2 | 5 | 10 | Amber | PM | Cross-train backup resource | 2026-10-01 | Project
Issue | Reconciliation mismatch in test cycle 2 | 5 | 4 | 20 | Red | Data Lead | Root-cause and re-run | 2026-09-16 | Programme
Assumption | Downstream systems accept batch format unchanged | 2 | 3 | 6 | Green | Tech Lead | Confirm with downstream owner | 2026-09-22 | Project
Green
Green
Green
Green
Green
Green

## 03 Executive RAID Summary
Executive RAID Summary
RAID ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Top Item | Business Impact | Trend | Owner | Decision Needed | Target Resolution
UAT reconciliation mismatch | Go-live exposure | Deteriorating | BI Lead | Confirm contingency | 2026-09-20
Key resource attrition risk | Delivery capacity | Stable | PM | Approve backfill budget | 2026-09-25

## 04 Technical Migration RAID
Technical Migration RAID
RAID ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Domain | Risk/Issue | Data/System | Environment | Probability | Impact | Score | Mitigation | Fallback | Owner
Data | Risk | Finance feed | UAT | 4 | 5 | 20 | Reconcile sample early | Rollback extract | Data Lead
Infrastructure | Issue | Cutover environment | Staging | 3 | 4 | 12 | Add capacity buffer | Extend window | Infra Lead

## 05 RAID Scoring Guide
RAID Scoring & Definitions Guide
RAID ¦ Reference Guide - probability/impact scale and RAID definitions
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
RAID Element | Definition
Risk | An uncertain future event that, if it occurs, would affect objectives. Always scored probability x impact.
Assumption | Something believed true for planning purposes but not yet confirmed. Must be validated or it becomes a risk.
Issue | A risk that has materialised, or a current problem with no uncertainty attached. Needs immediate action, not scoring.
Dependency | A piece of work, decision or resource owned outside the project's direct control, needed to proceed.
Score | Probability / Impact Meaning
1 | Rare / Negligible
2 | Unlikely / Minor
3 | Possible / Moderate
4 | Likely / Major
5 | Almost Certain / Severe
Score Range | RAG
1-6 | Green
7-14 | Amber
15-25 | Red

## 06 Assumptions Log
Assumptions Log
RAID ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Assumption | Rationale | Owner | Validation Method | Validate By | Status | Impact if Invalid
Test data mirrors production volumes | Needed for accurate performance testing | QA Lead | Compare row counts to prod extract | 2026-09-20 | Open | Performance results unreliable
Downstream systems accept batch format unchanged | No change request raised by downstream owner | Tech Lead | Confirm in writing with downstream team | 2026-09-22 | Open | Rework of interface mapping

## 07 RAID Trend Tracker
RAID Trend Tracker
RAID ¦ Live counts calculated from the Scored RAID Register
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Week Of | Open Risks | Open Issues | Red Items | Amber Items | Green Items
2026-09-08 | 2 | 1 | 1 | 2 | 7