## 00 Index
Status Reporting Toolkit
Status Reporting ¦ DeliverIQ Open PM Toolkit - Area Workbook
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Sheet | Template | Purpose
01 OnePage Weekly Status | Starter | Single-page team-level status for weekly circulation.
02 Executive Status Report | Executive | Summarised health, milestones, financials and asks for leadership.
03 Programme Status Pack | Executive / Programme | Roll-up across multiple projects for programme boards.
04 Agile Delivery Health Report | Agile | Sprint-level throughput and predictability metrics.
05 RAG Definitions & Thresholds | Reference | What Green/Amber/Red mean and when to change status.
06 Reporting Cadence & Calendar | Operational | Who reports what, to whom, and by when.
07 Status Metrics Glossary | Reference | Plain-English definitions of SPI, CPI, predictability and more.

## 01 OnePage Weekly Status
One-Page Weekly Status
Status Reporting ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Section | Current Update
Overall RAG | Amber
Executive Summary | Delivery on track for UAT entry; data reconciliation issue being resolved.
Achievements | Completed sprint 4; environment refresh done.
Next Week | UAT entry; vendor sign-off follow-up.
Risks | Key resource attrition (Amber).
Issues | UAT reconciliation mismatch (Red).
Dependencies | Finance feed certification (High).
Decisions Required | Approve contingency budget for parallel validation.

## 02 Executive Status Report
Executive Status Report
Status Reporting ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Section | Current Position | Trend | Executive Ask
Delivery Health | Amber | Stable | Awareness only
Milestones | UAT entry on track for 22 Sep | Stable | None
Financials | Forecast within 2% of budget | Stable | None
RAID | 1 Red issue, 2 Amber risks open | Deteriorating | Approve contingency budget
Decisions | Contingency validation path | - | Approve by 18 Sep

## 03 Programme Status Pack
Programme Status Pack
Status Reporting ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Project | RAG | Milestone Status | Top Risk | Dependency | Benefit Signal | Executive Action
Project A | Green | On Track | - | - | On track | None
Project B - Migration | Amber | UAT entry at risk | Reconciliation mismatch | Finance feed | At risk | Approve contingency
Project C - Platform Uplift | Green | On Track | - | Network cutover window | On track | None

## 04 Agile Delivery Health Report
Agile Delivery Health Report
Status Reporting ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Sprint | Sprint Goal | Planned | Completed | Carry-over | Blocked | Defects | Throughput | Predictability % | Actions
Sprint 1 | Foundation setup | 20 | 18 | 2 | 1 | 3 | 18 | 90% | Carry blocked item to Sprint 2
Sprint 2 | Core integration build | 22 | 20 | 2 | 0 | 1 | 20 | 90.91% | None
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0 | 0 | 0

## 05 RAG Definitions & Thresholds
RAG Definitions & Thresholds
Status Reporting ¦ Reference Guide
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
RAG | When To Use It
Green | On track: no open Red/Amber risks or issues threaten the next milestone or budget.
Amber | At risk: an issue or risk could affect the next milestone/budget if not actively managed this week.
Red | Off track: a committed milestone, budget, or scope commitment has already slipped or will without intervention.
Rule of Thumb | Guidance
Never skip Amber | Green should not jump straight to Red - Amber signals the trend early.
State the 'why' | Every non-Green status needs one sentence naming the specific driver.
Downgrade fast, upgrade slowly | Change to Red as soon as evidence appears; only return to Green once the fix is proven.

## 06 Reporting Cadence & Calendar
Reporting Cadence & Calendar
Status Reporting ¦ DeliverIQ Open PM Toolkit
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Report | Audience | Frequency | Owner | Day / Time | Format
One-Page Weekly Status | Team + Delivery Lead | Weekly | Project Manager | Friday 12:00 | Email
Executive Status Report | Sponsor + SteerCo | Fortnightly | Delivery Lead | Mon 09:00 | SteerCo pack
Programme Status Pack | Programme Board | Monthly | Programme Manager | 1st Thu | Board deck
Agile Delivery Health Report | Product Owner + Team | Per Sprint | Scrum Master | Sprint review | Dashboard

## 07 Status Metrics Glossary
Status Metrics Glossary
Status Reporting ¦ Reference Guide
Free reusable template - CC BY 4.0 - Sheuli A Mukherjee / DeliverIQ
Metric | Definition
SPI (Schedule Performance Index) | Earned Value / Planned Value. Above 1.0 means ahead of schedule, below 1.0 behind.
CPI (Cost Performance Index) | Earned Value / Actual Cost. Above 1.0 means under budget for work delivered.
Predictability % | Story points completed / story points committed at sprint start. Target is typically 80-100%.
Throughput | Number of items (stories, tickets) completed in a sprint or period.
Carry-over | Committed work not completed in the sprint and moved to the next one - a leading indicator of over-commitment.
Burn rate | Actual spend per period compared to the budgeted spend per period.